## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | This set of tests is intended to check main functionality developed
Apptitude Test Plan |  |  |  | Windows 10, 8, 8.1, 7 Android 8.0 and later
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Open Game | GUI | Launch Game application |  | Display Game Menu Page | Display Game Menu Page | Pass
2 | 1 | TC.002 | Select Play | GUI | Select Play from Menu |  | Display Game Page | Display Game Page | Pass
2.01 | 1 | TC.003 | Begin Game | GUI | Select Begin button |  | Begin Moving button Icons across screen | Begin Moving button Icons across screen | Pass
2.02 | 1 | TC.004 | Round Timer | GUI |  | Verify Correct Page Diplayed. Observe round timer label decrementing in seconds | Timer label decreases by one second each second | As expected for the first round. Timer decrements by +1 second each successive round | Fail
2.03 | 1 | TC.005 | Retry Button | GUI | Select Rettry button |  | Round begins again | Round begins again | Pass
2.04 | 1 | TC.006 | Letter prompt | GUI | Select Begin Button |  | Prompt Appears in top centre label | Prompt Appears in top centre label | Pass
2.05 | 1 | TC.007 | Arithmetic prompt | GUI | Select Begin Button |  | Prompt Appears in bottom centre label | Prompt Appears in bottm centre label | Pass
2.06 | 1 | TC.008 | Frames Tapped | GUI | Tap red, yellow or green frame | Check if the respective coloured button is within the frame area and shakes button if true, Frame bounces on tap. | Frame bounces on tap, button if within frame bounds will shake and return to starting location. | Frame bounces on tap. Button continues to move and collision is not deteected. | Fail
2.07 | 1 | TC.009 | Keypad | GUI | Type on keypad. |  | Enters test into arithmetic label. | Enters test into arithmetic label. | Pass
2.08 | 1 | TC.010 | Go Button | GUI | Press 'GO' button on calculator keypad. | Check if the answer is correct and load the nect sum into the label. | Enters new sum prompt. Accrues score for correct answer. | Enters new sum prompt. Does not add a score for correct answer. | Fail
2.09 | 1 | TC.011 | Letter Button Answers | GUI |  | Checks if selected button is the same as the initial prompt. | Buttons populate with possible answers after a delay, when pressed will add score for correct answer selected. | Buttons populate with possible answers without delay. No score for correct answer selected. | Fail
2.1 | 1 | TC.012 | Back Arrow | GUI | Press Back arrow from anywhere in App |  | Return user to previous page | Return user to previous page | pass
3 | 1 | TC.013 | About Page | GUI | Select About from Menu |  | Display About Page | Display About Page | Pass
3.1 | 1 | TC.014 | About Menu | GUI | Slide left/right in about page menu |  | Display pages in about menu | Display pages in about menu | pass
4 | 1 | TC.015 | Tutorial Page | GUI | Select Tutorial from Menu |  | Display Tutorial page | Display Tutorial page | pass
4.1 | 1 | TC.016 | Tutorial Menu | GUI | Slide left/right in Tutorial menu |  | Display pages in the Tutorial Menu | Display pages in about menu | pass
5 | 1 | TC.017 | Options Page | GUI | Select Options from Menu |  | Display options page | Display options page | pass
5.1 and 5.2 | 1 | TC.018 | Option Left/Right | GUI | Flick the switch in Options page | Checks current view orientation | Flips Orientation of Game page View. Reflects this with an image change in the options page. Updates tect in Optins page to reflect current game ciew oriwntation. | Flips Orientation of Game page View. Reflects this with an image change in the options page. Updates tect in Optins page to reflect current game ciew oriwntation. | pass
6 | 1 | TC.019 | Game Stats Page | GUI | Select Game Stats from Menu | Checks local storage on device for game statistics | Displays game stats in a scrollable list. | Displays default data, not loading from file. | fail

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%